## Sheet1
updated/recovered Punchlist
Item | Action Type | Version | Lead | Assists | Status (Done, Started, To Do), Actually, this is what is it | Deadline, Actually, these are routinely ignored, rather flagged huge needs | Dec 2014, Jan 2015
Convert to new code base Windows | Development | 1.5 | Gavin |  | running on build 04/29/14 | FINISHED
Convert to new code base Linux | Development | 1.5 | Gavin |  | running on build 12/01/13, need to align with Windows build | Done
Convert to new code base Mac | Development | 1.5 | Gavin |  | running on build, need to align with Windows build | In progress
Test new code base to old base run |  | 1.5 | Rob, Sarah |  |  | In progress
Check version compatability |  |  | Rob, Sarah |  |  | In progress
Finalize new Functional Group structure | Development | 1.5 | Gavin |  | Revised send to group for feedback | Done
Finalize new Fleet structure | Development | 1.5 | Gavin |  | Revised send to group for feedback | Done
Update biol.prm file for new group structure | Development | 1.5 | Gavin |  | R scripts write csv files in new structure for insertion of updated data values. List of biological parameters made. Decide which to prioritize and which can remain from old version | Mostly done, save prey | see prey/diet
Update initial condition files for new group structure | Development | 1.5 | Gavin |  | R scripts write csv files in new structure for insertion of updated data values. List of biological parameters made. Compile biomass data for new group structure, can do using Sean's R code for skill assessment, Gavin to provide Sean with codes for new group structure. | avg B from last 10 years for operating model; mostly done | update AAC, diets
Update harvest.prm file for new group structure | Development | 1.5 | Gavin | Sean | Manipulation of file to accommodate new group structure. Decide what effort models needed, whether to go for fixed catches, fixed effort, dynamic effort, etc. Compile catch and effort time series for new group structure | done? | update catch TS for historical
Develop Tuning and skill criteria | Development | 1.5 | Rob, Sarah | Erik, Sean, Gavin | Identify key criteria and output standards to identify best tuned models | In progress | needs diet and catch sorted
Regular meetings | Meeting | 1.5 | Gavin |  | Status updates | Set up
Tuning | Testing | 1.5 | Gavin? | ? | Tests to ensure new version behaving. BMSY tests, historic catch levels, etc. | In progress
Running base scenarios | Implementation | 1.5 |  |  | Baseline with current effort/catch levels, current estimated FMSYs, etc. Results needed for Tech Memo.
Atlantis Skill Assessment | Manuscript | 1.5 | Erik | Sean, all |  | In progress
Assessment of Indicator trends and thresholds | Manuscript | 1 | Gavin |  | In progress | In progress
Indicator-based assessment and control rule | Development | 1.5 | Gavin |  | R code written. Converstion to C in Atlantis code in progress | Code done, next test needed
MSE testing of indicator-based controle rule | Manuscript | 1.5 | Gavin |  | In prep | In progress
Technical Report | Manuscript | 1.5 | Gavin |  | Tech Memo description of v.1.5. Gavin to finish
Mtg before Gavin leaves | Meeting | 1.5 | Gavin |  | Last week of Aug | Done
Initiate Search for next modeler | Implementation | 2 | Jason |  |  | In progress
Insert full Econ (updated I/O, etc.) modules | Development | 2 | ?
Full MSE Test | Testing |  | Rob? | Erik, all | Not sure what is meant by this
Closure Scenarios Test | Testing | 1.5/2.0 | Erik |  |  | Waiting for 1.5
Starvation Mortality | Development |  | Rob? |  |  | in progress | Test thresholds
check pPrey |  | 1.5 | Rob
Check box assignments for biological groups | Development | 1.5 | ? |  |  | mostly done, double check | map boxes
Check spp locations and distributional proportions relative to box structure | Development | 1.5 | ? |  |  | mostly done, double check
Set up historical runs | Testing | 1.5 | Sean |  | See harvest prm above |  | wrt catch
Get full TS for initial conditions | Development | 1.5 | Sean |  | See harvest prm above |  | wrt catch
Revisit Fleet Dynamics | Development | 2.0? | ? |  | Need to discuss timeline/prioritization depending on staffing
Insert updated climate change and OA modules | Development | 2 | ?
New Box Structure | Development | 2.0? | ? |  | Need to discuss timeline/prioritization depending on staffing
New Hydrodynamics | Development | 2.0? | ? |  | Need to discuss timeline/prioritization depending on staffing
Rework Nutrients | Testing | 2.0? | ? |  | Need to discuss timeline/prioritization depending on staffing |  | double check
Migration rates and patterns | Development | 2.0? | ? |  | Need to discuss timeline/prioritization depending on staffing
Movement | Development | 2 | ?
Test VES-V viewer | Implementation | any | All |  |  | ongoing | ongoing
revisit pH forcing file | Development | 1.5 | ?
Climate scenarios |  | 1.5 | ? |  | Common, std scenarios for broad community
Fisheries Scenarios |  | 1.5 | ? |  | Common, std scenarios for broad community
Indicators Scenarios |  | 1.5 | ? |  | Common, std scenarios for broad community
MUM Scenarios |  | 1.5 | ? |  | Common, std scenarios for broad community
Spatial Scenarios |  | 1.5 | ? |  | Common, std scenarios for broad community
Economics/Fleet Behavior |  | 1.5 | ? |  | Common, std scenarios for broad community
Sensitivity analysis |  | 1.5 | ? |  | Common, std scenarios for broad community
Skill assessment |  | 1.5 | ? |  | Common, std scenarios for broad community
update AAC |  | 1.5 | Rob | Sean, Gavin | pull fhdbs, run through AAC, update
Update diagnostics more extensively |  | 1.5 |  |  | see examples from NoBa
Before Jan 12 mtg
Get new cod base and ancillary files on everyone's computers, and running
Finalize skill assessment
Test compatability of new code base-- baseruns with both features
Get spatial scenarios ready to run , if not some already
Test starvation, pPrey issues
Revisit and provide augmenting diagnostic packages (r scripts)
check Pprey matrix and assumptions
check catch converted to atlantis form
While at Jan 12 meeting
review status
confirm compatability
run some scenarios
start tuning
walk through rest of punch list